## Slide 1
LCLS-II SRF Commissioning
Sebastian Aderhold
for the SRF commissioning team
11 October 2022, TTC2022 Aomori

## Slide 2: Outline
LCLS-II Facility Overview, Scope, and Parameters
Installation
Cryogenic Systems & Cool Down
SRF and Cryomodule Commissioning
SC Beam Commissioning
Summary

## Slide 3: LCLS-II Facility Overview, Scope, and Parameters
1

## Slide 4
LCLS-II @ SLAC
SLAC is developing an upgrade of its Linac Coherent Light Source (LCLS) that will be at the forefront of X-ray science.
LCLS-II will provide a major jump in capability:
  Increasing from 120 pulses per second to 1 million pulses per second.
  Enabling researchers to perform experiments in a wide range of fields that are currently impossible.
  The unique capabilities of LCLS-II will yield a host of discoveries to advance technology, new energy solutions and our quality of life.

## Slide 5
LCLS-II
New Injector and
New Superconducting Linac
Existing Bypass Line
New Transport Line
Two New Undulators
And X-Ray Transport
Reconfigure Near Experiment Hall
New Cryoplant
Remove SLAC
Linac from
Sectors 0-10

## Slide 6: Linac & FEL Layout
Photocathode Gun
750 keV electrons
RF Photocathode Gun
35 1.3 GHz Cryomodules
2 3.9 GHz Cryomodules

## Slide 7: LCLS-II Technical Parameters
Performance Measure | Threshold | Objective
Variable gap undulators | 2 (soft and hard x‑ray) | 2 (soft and hard x‑ray)
Superconducting linac-based FEL system |  | 
Superconducting linac electron beam energy | 3.5 GeV | ≥ 4 GeV
Electron bunch repetition rate | 93 kHz | 929 kHz
Superconducting linac charge per bunch | 0.02 nC | 0.1 nC
Photon beam energy range | 250–3,800 eV | 200–5,000 eV
High repetition rate capable end stations | ≥ 1 | ≥ 2
FEL photon quantity (10-3 BW) per bunch | 5x108 (10x spontaneous) @2,500 eV | > 1011 @ 3,800 eV
Normal conducting linac-based system |  | 
Normal conducting linac electron beam energy | 13.6 GeV | 15 GeV
Electron bunch repetition rate | 120 Hz | 120 Hz
Normal conducting linac charge per bunch | 0.1 nC | 0.25 nC
Photon beam energy range | 1–15 keV | 1–25k eV
Low repetition rate capable end stations | ≥ 2 | ≥ 3
FEL photon quantity (10-3 BWa) per bunch | 1010 (lasing @ 15 keV) | > 1012 @ 15 keV
Achieved

## Slide 8: LCLS-II Technical Parameters
Performance Measure | Threshold | Objective
Variable gap undulators | 2 (soft and hard x‑ray) | 2 (soft and hard x‑ray)
Superconducting linac-based FEL system |  | 
Superconducting linac electron beam energy | 3.5 GeV | ≥ 4 GeV
Electron bunch repetition rate | 93 kHz | 929 kHz
Superconducting linac charge per bunch | 0.02 nC | 0.1 nC
Photon beam energy range | 250–3,800 eV | 200–5,000 eV
High repetition rate capable end stations | ≥ 1 | ≥ 2
FEL photon quantity (10-3 BW) per bunch | 5x108 (10x spontaneous) @2,500 eV | > 1011 @ 3,800 eV
Normal conducting linac-based system |  | 
Normal conducting linac electron beam energy | 13.6 GeV | 15 GeV
Electron bunch repetition rate | 120 Hz | 120 Hz
Normal conducting linac charge per bunch | 0.1 nC | 0.25 nC
Photon beam energy range | 1–15 keV | 1–25k eV
Low repetition rate capable end stations | ≥ 2 | ≥ 3
FEL photon quantity (10-3 BWa) per bunch | 1010 (lasing @ 15 keV) | > 1012 @ 15 keV
Achieved
Parameter | LCLS-II
# 1.3 GHz CMs | 35
Operating Gradient | 16 MV/m
Required Q0 at Operating Gradient | 2.7x1010

## Slide 9: Installation
2

## Slide 10: Cryomodule Installation
Last CM (spare) Delivered in May 2021
CM Installation Complete February 2021

## Slide 11: Undulator Installation
Vertical Variable Gap SXR Undulator
Horizontal Variable Gap HXR Undulator
Delivery of X-Rays to Instruments Began in 2020

## Slide 12: Cryogenic Systems & Cool Down
3

## Slide 13
Plan to fully commission and operate LCLS-II with 1 of 2 installed cryoplants

## Slide 14: Cryoplant Commissioning Process
~ 30 Months
10 mths
4 mths
3 mths
7 mths
2.5 mths
3 mths
1.5 mths
UTILITIES
Electricity
Control Network
Water
Air
Nitrogen
Helium
AUXILIARIES
Recovery compressor
Gas Analyzer
Purifier
COMPRESSORS
4K Cold Box
LINAC Ready
LINAC @ 2 K
2 K Pump Down
LINAC @ 4 K
Cool Down
Aug. 15th 2019
Dec. 15th 2019
Mar. 15th 2020
Jan. 15th 2021
Oct. 15th 2021
Jan. 1st 2022
Mar. 30th 2022
May 15th 2022

## Slide 15: Cool Down & Pump Down to 2 K
Cool down of the entire linac was completed in ~5 days!
A rate of 2-3 K/hour was maintained over that duration
Cool down was near-fully automated by the cryogenic controls system
After multiple attempts, stable operation at 2 K was achieved only 11 days later
2-3 K/hr
Cavity Temperatures During Cool Down

## Slide 16: SRF and Cryomodule Commissioning
4

## Slide 17: SRF Commissioning Process
Goal of initial cryomodule RF checkout was demonstration of capability for 3.5 GeV total energy gain (sum of all cavities operated individually and without beam)
Verified function of all relevant CM components (tuners, piezos, magnets)
Watch temperature, vacuum and radiation sensors for excursions to catch any problems that develop
  Live plots of 2 power coupler temps, 2 HOM coupler temps, coupler manifold vacuum, insulating vacuum and beamline vacuum, readout of DecaRad radiation monitoring

## Slide 18: SRF Commissioning Process
Per cavity:
Characterization of Solid State Amplifier (automated script mapping drive vs. output power
Tuning cavity to resonance (record initial frequency and steps to tuned for later reference), activate piezo tuner and verify functionality
Cavity signal calibration in pulsed mode: determine loaded Qext and scaling for cavity pickup probe signal

## Slide 19: SRF Commissioning Process
Cavity ramp up in SELA
Initial ramp up of cavity is in SELA mode (Self Excited Loop, CW with Amplitude feedback)
Increase amplitude until reaching the lower value of either 18MV or the useable amplitude as determined during acceptance test at partner lab, or if radiation exceeds 50mR/hr
Watch radiation monitors, temperatures and vacuums for excursions
In case of early cavity fault, retest cavity to 0.5MV below trip value and record as new usable amplitude.
1 hour run in SELAP
Switch cavity to SELAP mode (Self Excited Loop, CW with Amplitude and Phase feedback)
Max amplitude is the lower value of either 16.6MV or the useable amplitude as determined earlier
Verify amplitude and phase stability

## Slide 20: SRF Commissioning Process
12h full CM ‘unit test’
Upon completion of individual cavities set up of 12 hour run
  Monitoring of all relevant signals
  Turn on magnet package to design current
  Ramp all 8 cavities to operating amplitude
Maintain operation for up to 12 hours while moving on to individual cavity checkout on the next cryomodule
  Take cavity microphonics data while running.
Radiation physics group takes measurements outside shielding (at penetrations) during and at the cryomodule after the unit test

## Slide 21: Overall SRF Commissioning Status
Cryomodule commissioning has been very successful
98% of installed cavities fully operational (planned 94%)
Majority of testing included an admin limit of 18 MV/m
Total commissioned voltage exceeds design by >20%
Total Commissioned Cavity Voltage: 4.8 GV
Gradient Performance

## Slide 22: Gradient Performance
Gradient performance is in line with CM acceptance test measurements at FNAL and Jlab
No observable change in field emission onsets or magnitude from installation
Multipacting processing resulted in ~3 MV/m gain in stable gradient
Admin limits:
18 MV/m in commissioning
21 MV/m in acceptance test
Comparison with Acceptance Test
Change in FE Onset

## Slide 23: Multipacting Processing
Multipacting identified as a gradient limitation for LCLS-II cavities late in CM production
Observed as a short term stability at gradient in the band of 17-23 MV/m
Processing techniques developed and tested by LCLS-II-HE team and applied to a subset of cavities in the installed linac
  Consists of repeatedly quenching the cavity in CW mode with limited time (few seconds) for recovery
Repeated quenches
Stability achieved after ~35 minutes
Average gradient gain of ~3 MV/m observed in 37 cavities processed

## Slide 24: SC Beam Commissioning
5

## Slide 25: 100 MeV Injector Commissioning Completed
Establish beam and optimize to design specifications (emittance, charge, transmission)
Conduct beam containment system (BCS) certification
  Calibration of Beam Safety System devices at high repetition rate and bunch charge
  Beam current and beam loss monitors
1st Cryomodule providing beam energy to 100 MeV
Pulsed Magnet
Injector Diagnostics
SC linac 
Goals of Injector Commissioning:

## Slide 26: 100 MeV Injector Performance
Injector electron beam orbit
250 pC, 100% transmission
100 MeV electron beam image
Excellent Injector emittance: 0.6x0.8 µm

## Slide 27: Schedule Outlook
1st Light Milestone is anticipated in January of 2023
Achievement of Threshold KPPs 
Ready to begin routine delivery of x-rays to the instruments 

## Slide 28: Summary
LCLS-II commissioning is progressing well
Cool down of the superconducting linac went very smoothly and was complete in May 2022
Injector and 100 MeV commissioning has produced a beam of excellent quality
Cryomodule performance has been excellent, showing no degradation to cavity performance from installation at SLAC
The next few months will be very exciting!

## Slide 29
Thanks for your attention!
Special thanks to the entire LCLS-II collaboration for all their hard work to make this possible!

## Slide 30
Backup

## Slide 31: LCLS-II Technical Systems
Cryoplant #1 and Cryogenic Distribution
Injector Commissioning 100 MeV
SC linac and beam transport to Electron beam dump
Spreader system
SXR undulator beam line
HXR undulator beam line
X-Ray transport beamlines
X-Ray instruments

## Slide 32: Electron Gun and NC Beam Line Installation
Electron source beamline was built by LBNL (APEX Gun)
Laser system was manufactured by Amplitude:
    Oscillator operates at 46.43MHz
    Modulator selects pulse rate from 0 to 1MHz
    Conversion from IR to UV is 8-20%
Commissioned e-source (2018-2020), including several upgrades (e.g. tuners, additional collimators)
Completed in 2018, ready for source commissioning
Electron Gun cavity

## Slide 33: NC Linac Based Commissioning
3

## Slide 34: Completed Scope – NC Based Commissioning
750 keV Gun and laser system fully commissioned
Low energy beamline (LEB)
Loadlock for photocathode swaps
HXR Undulator
SXR Undulator
HXRSS-II
SXRSS-II (Ops)

Electron Gun
Beam Transport
Undulators
Linac to Undulators (LTUS, LTUH)
CLTS (Ops) beamline allowed early commissioning of SXR systems:
  Beam Transport
  Undulators and Instruments
Cu-Linac operation allowed commissioning of warm beamline systems, undulators, and instruments
Notes: CLTS: Copper Linac to Soft
LTUS Linc to Undulator(S-Soft, H- Hard)

## Slide 35: Early Injector Commissioning Completed in 2018
Gun chamber
Cathode
BEAM
Cathode manipulator
(housing and arm)
Trolley manipulator (housing and arm)
Cathode Insertion Assembly
Airlock
Airlock Gate Valve
Loadlock-to-gun Gate Valve
Suitcase Gate Valve
Cathode Suitcase
Top View
F. Zhou et al, “First Commissioning of the LCLS-II CW Injector Source,” presented at IPAC ‘19, Melbourne, Australia, May 2019, TUPTS106